## Sheet1
BÁO CÁO TIẾN ĐỘ CÔNG VIỆC
STT | Mô tả chức năng | Start Date | End Date | Status
1 | Khảo sát bài toán recommend News | 2023-05-20 | 2023-05-23 | Done
2 | Phân tích bài toán recommend News | 2023-05-20 | 2023-05-23 | Done
3 | Crawl data News | 2023-05-22 | 2023-05-23 | Done
4 | Tìm hiểu về mô tả dữ liệu | 2023-05-23 | 2023-05-23 | Done
5 | Kiểm tra sơ bộ dữ liệu | 2023-05-24 | 2023-05-24 | Done
6 | Chuấn hóa News | 2023-05-23 | 2023-05-25 | Done
7 | Đề xuất các mô hình recommend News | 2023-05-25 | 2023-05-25 | Done
8 | Chọn ra 1 – 3 mô hình recommend News | 2023-05-29 | 2023-05-30 | Done
9 | Thống nhất giải pháp xây dựng mô hình recommend News | 2023-05-30 | 2023-05-31 | Done
10 | Xây Dựng mô hình Kmeans | 2023-05-30 | 2023-06-01 | Done
11 | Xây Dựng mô hình embedding chữ tiếng việt | 2023-05-31 | 2023-05-31 | Done
12 | Traning Kmeans mỗi nhãn | 2023-05-31 | 2023-05-31 | Done
13 | Đồng bộ nhãn phân cụm | 2023-06-01 | 2023-06-01 | Done
14 | Embeding content news | 2023-06-02 | 2023-06-05 | Done
15 | Embeding title news | 2023-06-02 | 2023-06-05 | Done
16 | Embeding sumary news | 2023-06-02 | 2023-06-05 | Done
17 | Xây dựng luồng RCM | 2023-06-05 | 2023-06-08 | Done
18 | Test mô hình | 2023-06-08 | 2023-06-09 | Done
19 | Khảo sát bài toán recommend Voucher | 2023-06-08 | 2023-06-09 | Done
20 | Phân tích bài toán recommend Voucher | 2023-06-08 | 2023-06-09 | Done
21 | Tìm hiểu về mô tả dữ liệu Voucher | 2023-06-12 | 2023-06-12 | Done
22 | Kiểm tra sơ bộ dữ liệu Voucher | 2023-06-10 | 2023-06-10 | Done
23 | Kiểm tra missing values | 2023-06-12 | 2023-06-12 | Done
24 | Xử lý missing dữ liệu | 2023-06-12 | 2023-06-12 | Done
25 | Encode các trường định danh của dữ liệu | 2023-06-13 | 2023-06-13 | Done
26 | Chuấn hóa dữ liệu | 2023-06-13 | 2023-06-13 | Done
27 | Đồng Bộ dữ liệu | 2023-06-14 | 2023-06-15 | Done
28 | Sinh Dữ liệu huấn luyện | 2023-06-14 | 2023-06-15 | Done
29 | Chia train test dữ liệu | 2023-06-15 | 2023-06-15 | Done
30 | Embedding Features | 2023-06-15 | 2023-06-16 | Done
31 | Đề xuất các mô hình recommend item | 2023-06-15 | 2023-06-16 | Done
32 | Chọn ra 1 – 3 mô hình recommend item | 2023-06-15 | 2023-06-16 | Done
33 | Thống nhất giải pháp xây dựng mô hình recommend item | 2023-06-16 | 2023-06-19 | Done
34 | Xây dựng Data Loader | 2023-06-16 | 2023-06-19 | Done
35 | Xây dựng model Deep-wide Recommend System | 2023-06-16 | 2023-06-19 | Done
36 | Trainining Deep-wide Recommend System | 2023-06-20 | 2023-06-20 | Done
37 | Fine-tune model Deep-wide Recommend System | 2023-06-20 | 2023-06-20 | Done
38 | Test model Deep-wide Recommend System | 2023-06-20 | 2023-06-20 | Done